SCSC Church Project Timeline

| MONTH | TASKS |
| --- | --- |
|  | Churches may apply any time before the deadline. |
| July-August (Conference) | Church/Project application materials available at Conference. |
| September | Church/Project Application materials available online at: www.seventhdaybaptist.org/ministries/womens-board-scsc Begin praying about having an SCSC project at your church Begin the discussion in your church about having an SCSC project |
| Fall | Hosting an SCSC project must be approved by action of the church. If your church hears God’s call to have an SCSC project, put this on the agenda for your annual church business meeting. At your next church business meeting, vote on: Hosting an SCSC project A budget for local SCSC expenses A Project Director (PD) and small SCSC church committee for planning and support. |
| January | PD and church SCSC committee complete and send in application. Jan 29th Church/Project Applications due Mail to Helen Goodrich, SCSC, P.O. Box 164, North Loup, NE 68859 |
| March | March 1st- Project Acceptance and team notification to churches, PD and church SCSC committee Begin praying regularly for the project, leaders and students. Recruit prayer partners for the PD and the church project. Begin planning for student introductions to the church, housing, meals, bedding, transportation, any entertainment or sightseeing, activities with the church and community, love gift and farewell celebration. |
| April | Project Director and local SCSC Committee: Work out the details of the project grid. Talk with camp directors, pastor(s), Sabbath School supervisors, Youth program leaders Gather all needed materials and information for the SCSC team Finalize transportation plans and purchase of tickets for PD trip to and from SCSC training. |
| May | Project Director and local SCSC committee: Finalize plans from March list. Finalize grid details and send a copy to the appointed SCSC Training Staff member to look over prior to training. Gather all needed materials for PD to take to training, including phone numbers of all supervisors who will be working with the SCSC Team. |
| June | June 14th PD travels to SCSC Training, arriving to airport as close to 4 p.m. as possible June 15-23 SCSC Training @ Harley Sutton, Alfred Station, NY (PDs onsite June 14-19) June 23- July 28, SCSC Team on Projects (4.5 weeks) |
| July | July 31-August 6 Seventh Day Baptist General Conference Midweek conference, PD joins denominational SCSC Committee, Training Director, and available SCSC Training staff for an evaluation luncheon (as planned by director). |

Revised 9/15 scl